## Todo
Date | Project | To Do | Target Done Date | Progress (%) | Status | Problem | Issue? | Notes
2020-03-23 | GASPOL | Menanggapi email dari pak Agung, coba discuss directly dengan Aris terkait db hardening | 2020-03-23 | 75% | Instalation database done, current situation is waiting for queue project | Queue project
|  | Discuss directly ke Bandi terkait email dari Ridho Sec | 2020-03-23 | 100% | Will be inform for detail server, tbd | Previously, I already sent detail server
|  | Email Bandi to open priviledge and set to cyberark VM db gaspol | 2020-03-23 | 100% | Done
|  | follow up gaspol development untuk php version nya | 2020-03-23 | 0% | Not described yet |  |  | Tommorrow will be follow up
| CLICK | Follow up ke team perkembangan selanjutnya apa | 2020-03-23 | 100% | There is some cases in datatable update | Try to fixing tonight
|  | Make sure tidak ada task sprint 2 yang pending | 2020-03-23 | 50% | Until know on schedule
| ATM | Follow up ke Kholish untuk proses deployment ATM di server Ridwan 10.16.8.102 | 2020-03-23 | 30% | Already get user access to server, some backend service already up in the serve, but for front end still got error 500
|  | Minta ke pak ruswanto untuk dibukakan akses ke gitlab | 2020-03-23 | 100% | Done
|  | Follow up ke Dessy terkait project ATM dan make sure by email bahwa development sudah done | 2020-03-24 | 0% | Not mailed yet
| Autodebet | Make sure ke pak ruswanto terkait koneksi ke 19.1.35.3 untuk vpn ats | 2020-03-23 | 100% | Done
| RNCS | follow up ke pak Ferry untuk production api sap dan make sure tidak ada parameter yang berubah | 2020-03-24 | 50% | Already get feedback from Varian about new production, and they ask for credential our project to register it to system
2020-03-24 | GASPOL | Follow up credential access db ke Aris | 2020-03-24 | 100% | Done
|  | Email ke Ridho setelah dapat credentian ke Aris | 2020-03-24 | 100% | Done
|  | Bantu follow up ke Nugroho | 2020-03-24 | 100% | Done
| CLICK | Follow up ke Winny utk UAT hari Kamis | 2020-03-24 | 100% | Done
|  | Follow up task yang masih pending | 2020-03-24 | 100% | Done
|  | Merging repository | 2020-03-24 | 100% | Done
| ATM | Cek server | 2020-03-24 | 50% | Case di konfigurasi php, harus ditrace lagi |  |  | Ridwan dan Parwono akan join zoom
|  | Follow up lagi ke Dessy | 2020-03-24 | 100%
| Autodebet | -
| RNCS | Bales email Varian | 2020-03-24 | 75%
|  | Create SARF utk registrasi user API | 2020-03-24 | 0%
2020-03-26 | GASPOL | Konfirmasi ke Lieta utk DB Gaspol | 2020-03-24 | 100% | Done
| CLICK | Merging repository | 2020-03-24 | 100% | Done
|  | UAT Sprint 2 | 2020-03-24 | 100% | Done
| ATM | Follow up server ATM | 2020-03-24 | 60% |  |  |  | Cek 1 by 1 module in order to run no bugs
| Autodebet | Follow up progrees autodebet | 2020-03-24 | 0% | Senin ready untuk UAT 4 bank |  |  | Pak Cahyo prepare docker agar dapat run optimal sesuai schedule
| RNCS | Create SARF utk registrasi user API SAP | 2020-03-24 | 100% | Done
|  | Make sure by email ke Pak Ferry tidak ada parameter yg berubah | 2020-03-24 | 100% | Done
2020-03-27 | GASPOL | Inform to IT Cloud (Bandi) to install webserver (nginx) in 2 vm Gaspol, detail will be email directly to Bandi | 2020-03-27 | 100% | Done
|  | Make sure Development URL run normally to team | 2020-03-27 | 100% | Done
| CLICK | Meeting internally to decide task to team | 2020-03-27 | 0%
|  | Make sure link url production run well | 2020-03-27 | 100% | Done
| ATM | Follow up running server in production | 2020-03-27 | 100% | Done
| Autodebet | Inform to Postpaid Team (Dessy and Mesti) for UAT on Monday 30 March 2020 | 2020-03-27 | 100% | Done
|  | check vpn for 10.1.35.40 Pak Cahyo | 2020-03-27 | 50% | Not respond yet from user
| RNCS | Follow up to Sukron to communicate with Dessy for test new data on API Production | 2020-03-27 | 70% | Not respond yet from user
|  | Follow up directly to Varian team (SAP) about paralley SARF | 2020-03-27 | 0% | Pending to make sure proxy api SAP put to one server
2020-03-30 | GASPOL | Hardening webserver | 2020-03-30 | 0%
| CLICK | Sprint Planning 3 | 2020-03-30 | 0%
| ATM | Follow up server ATM | 2020-03-30 | 0%
| Autodebet | UAT | 2020-03-30 | 0%
| RNCS | Move SAP Proxy to production | 2020-03-30 | 0%
| SMAS | Follow up to IT Operation for run normally after change Google API Key | 2020-03-30 | 0%
https://ftp.tugraz.at/tu-graz/vpn/
https://vpn-office.smartfren.com

## Skill List
1 | Programming Language
| Desktop | Web | Mobile | Backend
| Delphi 7 (E) | PHP Codeigniter (E) | Ionic (B) | Golang Native, Gokit (E)
| VB 6 (E) | HTML (E) | Flutter (B) | Java (I)
| Powerbuilder (I) | CSS (Native, Bootstrap) (E)
ColdFusion (B)
2 | Message Broker
Kafka (E)
3 | Queue System
ActiveMQ (I)
RabbitMQ(E)
4 | NoSql
Redis (I)
Elasticsearch (I)
MongoDB (E)
Cassandra (B)
5 | Repository
Gitlab (E)
Github (E)
Tortoise SVN (I)
6 | Architecture Programming
Monoltyh (E)
Microservice (E)
7 | System Communication
Rest API (E)
RPC (I)
8 | Database
Mysql (E)
SQL Server (E)
Oracle (E)
9 | Tools
Confluence (I)
B (Beginner)
I (Intermediate
E (Expert)